## Sheet1
ID		User Story / Story points	Imp	Estimated	How to demo	Notes
ex		As a < user role>, I want < goal> [so that<reason>]	1 till 10	5	do this, do that and check if right	Use this. Needs something. Etc

1		As a developer, I want a functioning work environment	-
	1,1	Install Windows	1	16
	1,2	Install Linux	1	8
	1,3	Install Third party Drivers	1	2
	1,4	Install Visual Studio on Windows	1	6
	1,5	Install IDE on Linux	6	8

2		As a user, I want to see a game window	-
	2,1	Create a window handler for Directx	1	1,5
	2,2	Create a window handler for OpenGL	3	1,5
	2,3	Create basic rendering for Directx	2	4
	2,4	Create basic rendering for OpenGL	4	6

3		As a user, I want to see objects and textures	-
	3,1	Create basic Camera	5	1
	3,2	Create a model loader	4	3
	3,3	Create a texture loader	6	2
	3,4	Object rendering Directx	5	6
	3,5	Object rendering OpenGL	7	8
	3,6	Object textureing Directx	8	8
	3,7	Object textureing OpenGL	10	4
	3,8	Billboarding Directx (Menu)	9	3
	3,9	Billboarding OpenGL (Menu)	11	5
	3,10	Billboarding Directx (freemoving and locked to camera)	10	8
	3,11	Billboarding OpenGL (freemoving and locked to camera)	11	10
	3,12	Particle effects Directx	11	?
	3,13	Particle effects OpenGL	12	?
	3,14	Skybox	14	2

4		As a user, I want to hear sounds when something happens.	-
	4,1	Create soundclass (fmod)	9	3		Load sounds, play sounds
	4,2	Create soundevent system	10	2
	4,3	Find soundfiles	12	4

5		As a user, I want to be able to start the game and use it's basic functions	-
	5,1	Create game foundation	4	2
	5,2	Create menuclass	8	4
	5,3	Create GameLogic class (base)	6	4		Control and load levels,starts a game
	5,4	Create inputhandler	5	2

6		As a user, I want to play the basic game	-
	6,1	Create gameplay class	7	10
	6,2	Create bricks (base function)	7	2
	6,3	Create ball (base function)	7	2
	6,4	Create pad (base function)	7	2
	6,5	Collission tests (2D)	8	2		in physics class
	6,6	Collission tests (Cylinder)	11	2		in physics class
	6,7	Collission tests (Sphere)	11	4		in physics class
	6,8	Object class	5	1
	6,9	Logic game classes planning	3	4		UML
	6,10	Timer	7	1

7		As a user, I want to play on different maps	-
	7,1	Create Maploading	8	2		and map class
	7,2	Map interpretation	8	5		in Map and gameplay classes
	7,3	Map switching	9	1		in Gamelogic
	7,4	Logic for handling the different types of maps*	10			in gameplay, boll, collision etc
	7,4A	Logic for scrolling maps	10	4
	7,4B	Logic for cylinder maps	10	6
	7,4C	Logic for sphere maps	10	8
	7,5	Create map images	9	6

8		As a user, I want variety in the gameplay	-
	8,1	Eventmanager system	10	4
	8,2	Implement effects and powerups*	12 till 14	12
	8,2A	Speed/Slow	12
	8,2B	Bigger/Smaller	12
	8.2C	Inverted controlls	14
	8,2D	Rotationspeed	14
	8,2E	Extra Liv	14
	8,2F	Shooting blocks	14
	8,3	Randomize effects and powerups	13	2
	8,4	Different events/effects deppending on maps*	13	20
	8,4A	Zappers	13
	8,4B	Local winds	13
	8,4C	Rising water	13
	8,4D	Waves	13
	8,4E	Eruptions	13
	8,4F	Fire balls	13
	8,4G	Earthquakes	13
	8,4H	Bumpers	13
	8,5	Additional physics*	12	6		Like gravity and wind
	8,5A	Wind physics	12	4
	8,5B	Gravity physics	12	2

9		As a player, I want an interesting story	-
	9,1	Plan story	15	4
	9,2	Cutscenes	15	4
	9,3	Map progression	9	2

10		As a player, I want the game to be bug free	-
	10,1	Bugfixing	1 till 15

11		As a developer, I want a organised and efficient project	-
	11,1	Sprint planning		7
	11,2	Daily Scrum meetings		10
	11,3	Sprint evaluation/demonstration		8
	11,4	Paperwork

				256